TEST MILESTONES

| Milestone | Effort (MD) | Start Date | End Date |
| --- | --- | --- | --- |
| Create Test Plan | 3 | 11/05/2026 | 13/05/2026 |
| Prepare Test Environment and Data | 4 | 14/05/2026 | 18/05/2026 |
| Design Unit Test Cases | 15 | 19/05/2026 | 31/07/2026 |
| Execute and Complete Unit Test Baseline | 12 | 01/06/2026 | 14/08/2026 |
| Design Integration Test Cases | 6 | 24/07/2026 | 21/08/2026 |
| Execute and Review Integration Test Round 1 | 4 | 22/08/2026 | 23/08/2026 |
| Analyze and Correct Integration Issues | 9 | 24/08/2026 | 09/09/2026 |
| Execute Integration Test Round 2 | 3 | 10/09/2026 | 11/09/2026 |
| Design System Test Cases | 5 | 17/08/2026 | 27/08/2026 |
| Execute and Review System Test Round 1 | 3 | 28/08/2026 | 29/08/2026 |
| Correct System Workflow Issues | 7 | 30/08/2026 | 09/09/2026 |
| Execute System Test Round 2 | 2 | 10/09/2026 | 11/09/2026 |
| Execute Final Unit Regression | 3 | 12/09/2026 | 14/09/2026 |
| Prepare Acceptance Test | 3 | 12/09/2026 | 14/09/2026 |
| Execute Acceptance Test | 4 | 15/09/2026 | 15/09/2026 |
| Consolidate Defect Summary | 3 | 16/09/2026 | 17/09/2026 |
| Prepare Final Test Summary | 2 | 18/09/2026 | 18/09/2026 |
| Total | 88 |  |  |